## Overview
Project Name
Overview
Reference Information | Location | Comments
Use Cases & Requirements | [Link]
Reference Material | [Link]
Test Environment information | [Link]
End User Documentation | [Link]
Test Schedule | [Link]
Change Log | Person | Date | Test Instructions
Created Doc | Eric D | 2014-08-12
Test Results Summary (Auto Calculated) | Number | Percent
Total Test Cases Passed | 8 | 4.624%
Total Test Cases Failed | 5 | 2.89%
Total Test Cases Remaining | 160 | 92.49%
© Eric R. Dayal

## Add Customer
Test Info |  | Test Summary
Test Scenario | Search and add new drinks in database | Total Passed | 4
Test Environment | Development ;aptop | Total Failed | 3
|  | Total Remaining | 36
Test Case ID | Test Case Description | Expected Result | Test Data | Actual Result | Status | Tester | Date/Time | Comments
dom-001 | Search for existing drink by one ingredients | Drinks found | Mai Tai | Drinks found | Pass | Patt | 02-01-16 1:30pm
dom-002 | Search for existing drink by Two ingredients | Drinks found | Long Island Iced Tea | Drinks found | Pass | Patt | 02-05-16 2:30pm
dom-003 | Search for existing drink by Three ingredients | Drinks found | 57 chevy | data binding error | Fail | Patt | 02-05-16 5:00pm | Error: box linked incorrectly
dom-004 | Search for existing drink by Three ingredients | Drinks found | 57 Chevy | Drinks found | Pass | Patt | 02-05-16 7:30pm
dom-005 | Search for existing drink by name | Drinks found | MaiTai | No drink found | fail | Patt | 02-10-16 2:00pm | MaiTai was listed as Mai Tai (fixed data
dom-006 | Search for exsisting drink by name | Drink Found | Mai Tai | Drinks found | Pass | patt | 02-10-16 2:05pm
dom-007 | Add drink to list | Drink added | Dirty Bronx | Did not save | fAIL | pATT | 02-16-16 3:00PM | Fixing connection
dom-008 | Add drink to list | Drink added | Dirty Bronx |  | Not Started | Patt
dom-009 | login | login | Username PW |  | Not Started | Patt
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started

## Book Order
Test Info |  | Test Summary |  |  | Instructions |  |  | © Eric R. Dayal
Test Scenario | Add products, sales tax, and discounts | Total Passed | 2 |  | In the "Status" column, use Pass, Fail, or Not Started.
Test Environment | Sandbox instance | Total Failed | 1 |  | Totals and color highlighting will update automatically based on the Status column
Test Data Source | [link] | Total Remaining | 62
Test Case ID | Test Case Description | Expected Result | Test Data | Actual Result | Status | Tester | Date/Time | Comments
BO-0001 | Add products to the Order | Products added | Product 1, Product 2 | Products added | Pass | Eric D. | 01-02-14 1:30pm
BO-0002 | Calculate sales tax based on location | Sales Tax Calculated | Postal Code 78759 | Sales Tax is Zero | Fail | Eric D. | 01-02-14 1:35pm | Sales tax did not calculate properly
BO-0003 | Add a 10% discount to the order | Total decreased by 10% | 10% discount | Total decreased by 10% | Pass | Eric D. | 01-02-14 1:40pm
BO-0004 |  |  |  |  | Not Started
BO-0005 |  |  |  |  | Not Started
BO-0006 |  |  |  |  | Not Started
BO-0007 |  |  |  |  | Not Started
BO-0008 |  |  |  |  | Not Started
BO-0009 |  |  |  |  | Not Started
BO-0010 |  |  |  |  | Not Started
BO-0011 |  |  |  |  | Not Started
BO-0012 |  |  |  |  | Not Started
BO-0013 |  |  |  |  | Not Started
BO-0014 |  |  |  |  | Not Started
BO-0015 |  |  |  |  | Not Started
BO-0016 |  |  |  |  | Not Started
BO-0017 |  |  |  |  | Not Started
BO-0018 |  |  |  |  | Not Started
BO-0019 |  |  |  |  | Not Started
BO-0020 |  |  |  |  | Not Started
BO-0021 |  |  |  |  | Not Started
BO-0022 |  |  |  |  | Not Started
BO-0023 |  |  |  |  | Not Started
BO-0024 |  |  |  |  | Not Started
BO-0025 |  |  |  |  | Not Started
BO-0026 |  |  |  |  | Not Started
BO-0027 |  |  |  |  | Not Started
BO-0028 |  |  |  |  | Not Started
BO-0029 |  |  |  |  | Not Started
BO-0030 |  |  |  |  | Not Started
BO-0031 |  |  |  |  | Not Started
BO-0032 |  |  |  |  | Not Started
BO-0033 |  |  |  |  | Not Started
BO-0034 |  |  |  |  | Not Started
BO-0035 |  |  |  |  | Not Started
BO-0036 |  |  |  |  | Not Started
BO-0037 |  |  |  |  | Not Started
BO-0038 |  |  |  |  | Not Started
BO-0039 |  |  |  |  | Not Started
BO-0040 |  |  |  |  | Not Started
BO-0041 |  |  |  |  | Not Started
BO-0042 |  |  |  |  | Not Started
BO-0043 |  |  |  |  | Not Started
BO-0044 |  |  |  |  | Not Started
BO-0045 |  |  |  |  | Not Started
BO-0046 |  |  |  |  | Not Started
BO-0047 |  |  |  |  | Not Started
BO-0048 |  |  |  |  | Not Started
BO-0049 |  |  |  |  | Not Started
BO-0050 |  |  |  |  | Not Started
BO-0051 |  |  |  |  | Not Started
BO-0052 |  |  |  |  | Not Started
BO-0053 |  |  |  |  | Not Started
BO-0054 |  |  |  |  | Not Started
BO-0055 |  |  |  |  | Not Started
BO-0056 |  |  |  |  | Not Started
BO-0057 |  |  |  |  | Not Started
BO-0058 |  |  |  |  | Not Started
BO-0059 |  |  |  |  | Not Started
BO-0060 |  |  |  |  | Not Started
BO-0061 |  |  |  |  | Not Started
BO-0062 |  |  |  |  | Not Started
BO-0063 |  |  |  |  | Not Started
BO-0064 |  |  |  |  | Not Started
BO-0065 |  |  |  |  | Not Started
BO-0066

## Confirmation
Test Info |  | Test Summary |  |  | Instructions |  |  | © Eric R. Dayal
Test Scenario | Send confirmation and prepare invoice | Total Passed | 2 |  | In the "Status" column, use Pass, Fail, or Not Started.
Test Environment | Sandbox instance | Total Failed | 1 |  | Totals and color highlighting will update automatically based on the Status column
Test Data Source | [link] | Total Remaining | 62
Test Case ID | Test Case Description | Expected Result | Test Data | Actual Result | Status | Tester | Date/Time | Comments
CO-0001 | Send email order confirmation | Email sent | test@example.com | Email sent | Pass | Eric D. | 01-03-14 1:30pm
CO-0002 | View order details on the website | Order details visible | example.com/order123 | Order details visibile | Pass | Eric D. | 01-03-14 1:35pm
CO-0003 | Cancel the order from the website | Order is cancelled | Order 123 | Order not cancelled | Fail | Eric D. | 01-03-14 1:40pm | Error: Order cannot be updated. X89D97D
CO-0004 |  |  |  |  | Not Started
CO-0005 |  |  |  |  | Not Started
CO-0006 |  |  |  |  | Not Started
CO-0007 |  |  |  |  | Not Started
CO-0008 |  |  |  |  | Not Started
CO-0009 |  |  |  |  | Not Started
CO-0010 |  |  |  |  | Not Started
CO-0011 |  |  |  |  | Not Started
CO-0012 |  |  |  |  | Not Started
CO-0013 |  |  |  |  | Not Started
CO-0014 |  |  |  |  | Not Started
CO-0015 |  |  |  |  | Not Started
CO-0016 |  |  |  |  | Not Started
CO-0017 |  |  |  |  | Not Started
CO-0018 |  |  |  |  | Not Started
CO-0019 |  |  |  |  | Not Started
CO-0020 |  |  |  |  | Not Started
CO-0021 |  |  |  |  | Not Started
CO-0022 |  |  |  |  | Not Started
CO-0023 |  |  |  |  | Not Started
CO-0024 |  |  |  |  | Not Started
CO-0025 |  |  |  |  | Not Started
CO-0026 |  |  |  |  | Not Started
CO-0027 |  |  |  |  | Not Started
CO-0028 |  |  |  |  | Not Started
CO-0029 |  |  |  |  | Not Started
CO-0030 |  |  |  |  | Not Started
CO-0031 |  |  |  |  | Not Started
CO-0032 |  |  |  |  | Not Started
CO-0033 |  |  |  |  | Not Started
CO-0034 |  |  |  |  | Not Started
CO-0035 |  |  |  |  | Not Started
CO-0036 |  |  |  |  | Not Started
CO-0037 |  |  |  |  | Not Started
CO-0038 |  |  |  |  | Not Started
CO-0039 |  |  |  |  | Not Started
CO-0040 |  |  |  |  | Not Started
CO-0041 |  |  |  |  | Not Started
CO-0042 |  |  |  |  | Not Started
CO-0043 |  |  |  |  | Not Started
CO-0044 |  |  |  |  | Not Started
CO-0045 |  |  |  |  | Not Started
CO-0046 |  |  |  |  | Not Started
CO-0047 |  |  |  |  | Not Started
CO-0048 |  |  |  |  | Not Started
CO-0049 |  |  |  |  | Not Started
CO-0050 |  |  |  |  | Not Started
CO-0051 |  |  |  |  | Not Started
CO-0052 |  |  |  |  | Not Started
CO-0053 |  |  |  |  | Not Started
CO-0054 |  |  |  |  | Not Started
CO-0055 |  |  |  |  | Not Started
CO-0056 |  |  |  |  | Not Started
CO-0057 |  |  |  |  | Not Started
CO-0058 |  |  |  |  | Not Started
CO-0059 |  |  |  |  | Not Started
CO-0060 |  |  |  |  | Not Started
CO-0061 |  |  |  |  | Not Started
CO-0062 |  |  |  |  | Not Started
CO-0063 |  |  |  |  | Not Started
CO-0064 |  |  |  |  | Not Started
CO-0065 |  |  |  |  | Not Started
CO-0066